## Sheet1
Teaching week: | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | Easter holidays |  | 9 | 10 | 11
Sunday's Date: | 2016-10-02 | 2016-10-09 | 2016-10-16 | 2016-10-23 | 2016-10-30 | 2016-11-06 | 2016-11-13 | 2016-11-20 | 2016-11-27 | 2016-12-04 | 2016-12-11 | 2016-12-18 | 2017-01-22 | 2017-01-29 | 2017-02-05 | 2017-02-12 | 2017-02-19 | 2017-02-26 | 2017-03-05 | 2017-03-12 | 2017-03-19 | 2017-03-26 | 2017-04-16 | 2017-04-23 | 2017-04-30 | 2017-05-07
Task: | 2016-11-13: Sem 1; 2017-01-29: Sem 2
Christmas Holidays and Exams
Meeting with supervisors | bar: 2016-10-09
Draft a full Gantt chart | bar: 2016-10-09
Define roles for team members | bar: 2016-10-09 to 2016-10-16
Prepare presentation | bar: 2016-10-16 to 2016-10-23
Complete risk assessment | bar: 2016-10-16
Submit risk assessment | bar: 2016-10-16
Literature review | bar: 2016-10-16 to 2016-10-30
Presentation at research group level | bar: 2016-10-23 to 2016-10-30
Prepare Elevator Pitch | bar: 2016-10-23 to 2016-11-06
Complete form P2 | bar: 2016-10-23 to 2016-10-30
Simulation | bar: 2016-10-23 to 2016-11-06
Sketchings of test rig design/mechanism | bar: 2016-10-23 to 2016-10-30
Get manufacturing guideline from EDMC | bar: 2016-10-30 to 2016-11-06
Basic control system design | bar: 2016-10-30 to 2016-11-06
Determine aerofoil shape and sensor position | bar: 2016-11-06 to 2016-11-13
3D CAD modelling for test rig | bar: 2016-11-06 to 2016-11-13
Connect sensors and motors to Arduino | bar: 2016-11-06 to 2016-11-13
Elevator pitch presentations | bar: 2016-11-13
Submit form P2 | bar: 2016-11-13
Purchase sensors and relevant devices | bar: 2016-10-30 to 2016-11-13
Submit 3D test rig CAD models to EDMC | bar: 2016-11-13
Design and 3D CAD modelling for UAV | bar: 2016-11-13 to 2016-12-04
Assembly of test rig | bar: 2016-11-27 to 2016-12-04
Experimental testing on 2D model in wind tunnel | bar: 2016-12-04 to 2016-12-11
PID controller design | bar: 2016-12-04 to 2016-12-11
Submit 3D UAV part CAD models to EDMC | bar: 2016-12-04 to 2016-12-11
Complete form P3 | bar: 2016-12-11
Submit form P3 | bar: 2016-12-11
Complete Peer Feedback form (1) | bar: 2016-12-11
Assembly of UAV | bar: 2017-01-29 to 2017-02-12
Putting system onto the UAV | bar: 2017-02-12 to 2017-02-26
Experimental testing on UAV | bar: 2017-02-26; 2017-03-12 to 2017-03-19
Report write-up | bar: 2017-03-12 to 2017-04-16
Submit final report | 2017-04-16: 2016-04-21
Prepare presentation
Presentations and submit Peer Feedback Form (2) | 2016-10-02: 6-7/6/17
Design/Manufacturing members | 2016-12-18: * expected; 2017-03-12: UAV must be ready before this week
Coding/System design memebers | 2016-12-18: * completed
All members | 2016-12-18: * delayed